## Sheet1
Task | Task Name | Duration | Start
Init | Project Design | 7 | 2018-10-05
| Task Deconstruction and Plan | 5 | 2018-10-12
| UROP Proposal Composition | 7 | 2018-10-17
| Check Plan and Detail with Mentor | 7 | 2018-10-24
User App | UI | 3 | 2018-11-01
| Post Request | 7 | 2018-11-04
| Exchange GPS Data with Server | 14 | 2018-11-18
| Receive Video from Server | 21 | 2018-12-09
Server | Receive Request and Answer | 10 | 2018-11-01
| Exchange GPS Data with Server | 14 | 2018-11-18
| Send Video to User App | 21 | 2018-12-09
Control App | Exchange GPS Data with Server | 14 | 2018-11-18
| Decode Video to Datastream | 21 | 2018-12-09
| Control App: Send Video to Server | 21 | 2018-12-30
Vision | Train Multiple Model | 14 | 2018-11-24
| Integrate with Control App | 7 | 2018-12-15
| Realize Following Function | 28 | 2018-12-22
| Realize Self-Navigation Function | 28 | 2019-01-19
Integrate & Milestone | Integrate Request and Answer | 7 | 2018-11-11
| Integrate GPS Communication | 7 | 2018-12-02
| Integrate Video Transfer(Server and User) | 21 | 2018-12-30
| Integrate Video Transfer(Control and Server) | 21 | 2019-01-20
| Compare and Select Model on Testset | 7 | 2018-12-08
| Run the whole System with Basic Goal | 14 | 2019-02-10
| Improve System | 23 | 2019-02-24